## DEFECT_01
DEFECT_ID | DEFECT_01
MODULE | REGISTER
SUMMARY | FIRST NAME AND LAST NAME FIELDS ACCEPT NUMERIC AND SPECIAL CHARACTERS AND INVALID EMAIL FORMATS
DESCRIPTION | DURING REGISTRATION, FIRST NAME AND LAST NAME FIELDS ACCEPT NUMERIC AND SPECIAL CHARACTERS INSTEAD OF ONLY ALPHABETS. EMAIL FIELD ALSO ACCEPTS INVALID FORMATS WITHOUT VALIDATION.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION
STEP 2: GO TO THE REGISTER PAGE
STEP 3: ENTER NUMERIC/SPECIAL CHARACTERS IN FIRST NAME
STEP 4: ENTER NUMERIC/SPECIAL CHARACTERS IN LAST NAME
STEP 5: ENTER INVALID EMAIL FORMAT
STEP 6: ENTER PASSWORD AND CONFIRM PASSWORD
STEP 7: CLICK ON REGISTER
EXPECTED RESULT | FIRST NAME AND LAST NAME SHOULD ACCEPT ONLY ALPHABETS AND EMAIL SHOULD BE VALIDATED PROPERLY
ACTUAL RESULT | SYSTEM ACCEPTS INVALID INPUTS IN NAME AND EMAIL FIELDS
SEVERITY | CRITICAL
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1zM0JJDwYpfBaqic4CuuOUvaGQm5JSarz/view?usp=drive_link
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | ACER ONE 14
OS | WINDOWS
OS VERSION | 11
BROWSER | BRAVE
BROWSER VERSION | 1.88.136
BUILD VERSION

## DEFECT_02
DEFECT_ID | DEFECT_02
MODULE | PRODUCT LISTING / CART
SUMMARY | ADD TO CART BUTTON IS NOT DISPLAYED FOR SOME PRODUCTS
DESCRIPTION | ON THE PRODUCT LISTING PAGE, THE ADD TO CART BUTTON IS VISIBLE FOR SOME PRODUCTS BUT MISSING FOR OTHERS, EVEN THOUGH PRODUCTS ARE AVAILABLE FOR PURCHASE.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION
STEP 2: NAVIGATE TO PRODUCT LISTING PAGE
STEP 3: OBSERVE DIFFERENT PRODUCTS DISPLAYED
STEP 4: CHECK AVAILABILITY OF ADD TO CART BUTTON FOR EACH PRODUCT
EXPECTED RESULT | ADD TO CART BUTTON SHOULD BE DISPLAYED FOR ALL PRODUCTS THAT ARE AVAILABLE FOR PURCHASE
ACTUAL RESULT | ADD TO CART BUTTON IS MISSING FOR SOME PRODUCTS
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1KxtBkkcasg6GQoq48_TV7JW6VImUz1gO/view?usp=drive_link
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | ACER ONE 14
OS | WINDOWS
OS VERSION | 11
BROWSER | BRAVE

## DEFECT_03
DEFECT_ID | DEFECT_03
MODULE | CART / CHECKOUT
SUMMARY | CURRENCY SYMBOL IS MISSING IN PRICE DISPLAY DURING CHECKOUT
DESCRIPTION | ON THE SHOPPING CART AND CHECKOUT PAGE, THE PRICE VALUES ARE DISPLAYED WITHOUT ANY CURRENCY SYMBOL, WHICH MAKES IT UNCLEAR WHICH CURRENCY IS BEING USED.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION
STEP 2: ADD ANY PRODUCT TO THE CART
STEP 3: NAVIGATE TO THE SHOPPING CART PAGE
STEP 4: OBSERVE THE PRICE, SUBTOTAL, AND TOTAL VALUES
EXPECTED RESULT | ALL PRICE VALUES SHOULD DISPLAY WITH APPROPRIATE CURRENCY SYMBOL (E.G., $, ₹, €)
ACTUAL RESULT | PRICE VALUES ARE DISPLAYED WITHOUT ANY CURRENCY SYMBOL
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | UI DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1z8X-r1SrAtomLctNnmuP6Efsnj-VIWxb/view?usp=drive_link
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | ACER ONE 14
OS | WINDOWS
OS VERSION | 11
BROWSER | BRAVE

## DEFECT_04
DEFECT_ID | DEFECT_04
MODULE | SHIPPING / CHECKOUT
SUMMARY | SHIPPING COST IS ALWAYS DISPLAYED AS ZERO FOR ALL LOCATIONS
DESCRIPTION | IN THE ESTIMATE SHIPPING SECTION, THE SHIPPING COST IS DISPLAYED AS 0.00 FOR ALL SHIPPING METHODS AND LOCATIONS, INDICATING THAT SHIPPING CHARGES ARE NOT BEING CALCULATED CORRECTLY.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION
STEP 2: ADD A PRODUCT TO THE CART
STEP 3: NAVIGATE TO THE SHOPPING CART PAGE
STEP 4: GO TO ESTIMATE SHIPPING SECTION
STEP 5: SELECT ANY COUNTRY AND STATE/PROVINCE
STEP 6: CLICK ON ESTIMATE SHIPPING
EXPECTED RESULT | SHIPPING COST SHOULD BE CALCULATED AND DISPLAYED BASED ON SELECTED LOCATION AND SHIPPING METHOD
ACTUAL RESULT | SHIPPING COST IS DISPLAYED AS 0.00 FOR ALL LOCATIONS AND METHODS
SEVERITY | CRITICAL
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONALITY DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1cv-_AHvT1FyYD3J-mAeVGEKiporu2vH0/view?usp=drive_link
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | ACER ONE 14
OS | WINDOWS

## DEFECT_05
DEFECT_ID | DEFECT_05
MODULE | CHECKOUT / BILLING ADDRESS
SUMMARY | BILLING ADDRESS FIELDS ACCEPT INVALID DATA FORMATS
DESCRIPTION | IN THE BILLING ADDRESS SECTION, MULTIPLE FIELDS SUCH AS FIRST NAME, LAST NAME, CITY, ZIP CODE, AND PHONE NUMBER ARE ACCEPTING INVALID DATA FORMATS INCLUDING NUMERIC VALUES IN NAME FIELDS AND ALPHABETS IN NUMERIC FIELDS WITHOUT ANY VALIDATION.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION
STEP 2: ADD A PRODUCT TO THE CART
STEP 3: PROCEED TO CHECKOUT PAGE
STEP 4: SELECT NEW BILLING ADDRESS
STEP 5: ENTER INVALID DATA (E.G., NUMBERS IN NAME, ALPHABETS IN ZIP CODE/PHONE)
STEP 6: CLICK ON CONTINUE
EXPECTED RESULT | SYSTEM SHOULD VALIDATE ALL FIELDS AND ACCEPT ONLY CORRECT DATA FORMATS (E.G., ALPHABETS FOR NAMES, NUMBERS FOR ZIP AND PHONE)
ACTUAL RESULT | SYSTEM ACCEPTS INVALID DATA WITHOUT ANY VALIDATION ERRORS
SEVERITY | CRITICAL
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1gyvcbMceVP-WutuEiTre7gdJKIjgxpIB/view?usp=drive_link
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | ACER ONE 14

## DEFECT_06
DEFECT_ID | DEFECT_06
MODULE | PRODUCT DETAIL PAGE
SUMMARY | PRODUCT COLOR DOES NOT CHANGE WHEN SELECTING DIFFERENT COLOR OPTIONS
DESCRIPTION | ON THE PRODUCT DETAIL PAGE, SELECTING DIFFERENT COLOR OPTIONS DOES NOT UPDATE THE PRODUCT IMAGE OR VISUAL REPRESENTATION, MAKING IT DIFFICULT FOR USERS TO VIEW THE SELECTED COLOR VARIANT.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION
STEP 2: NAVIGATE TO ANY PRODUCT DETAIL PAGE WITH COLOR OPTIONS
STEP 3: SELECT DIFFERENT COLOR OPTIONS
STEP 4: OBSERVE THE PRODUCT IMAGE
EXPECTED RESULT | PRODUCT IMAGE OR VISUAL DISPLAY SHOULD UPDATE BASED ON SELECTED COLOR OPTION
ACTUAL RESULT | PRODUCT IMAGE REMAINS THE SAME EVEN AFTER SELECTING DIFFERENT COLOR OPTIONS
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | UI DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1rFbQBlSzrQr7ORWJXQ2iMQc4eWlBwEAk/view?usp=drive_link
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | ACER ONE 14
OS | WINDOWS
OS VERSION | 11
BROWSER | BRAVE

## DEFECT_07
DEFECT_ID | DEFECT_07
MODULE | PRODUCT DETAIL PAGE / WISHLIST
SUMMARY | ADD TO WISHLIST OPTION IS NOT AVAILABLE FOR SOME PRODUCTS
DESCRIPTION | ON CERTAIN PRODUCT DETAIL PAGES, THE ADD TO WISHLIST OPTION IS MISSING, PREVENTING USERS FROM SAVING THOSE PRODUCTS FOR FUTURE REFERENCE.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION
STEP 2: NAVIGATE TO DIFFERENT PRODUCT DETAIL PAGES
STEP 3: OBSERVE THE PRESENCE OF ADD TO WISHLIST OPTION
EXPECTED RESULT | ADD TO WISHLIST OPTION SHOULD BE AVAILABLE FOR ALL PRODUCTS
ACTUAL RESULT | ADD TO WISHLIST OPTION IS MISSING FOR SOME PRODUCTS
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1ZD8TFRXXdE0o6cojZYEWs2PgJnyQ_0Od/view?usp=drive_link
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | ACER ONE 14
OS | WINDOWS
OS VERSION | 11
BROWSER | BRAVE
BROWSER VERSION | 1.88.136

## DEFECT_08
DEFECT_ID | DEFECT_08
MODULE | PRODUCT DETAIL PAGE
SUMMARY | OUT OF STOCK STATUS IS NOT DISPLAYED FOR PRODUCTS
DESCRIPTION | ON THE PRODUCT DETAIL PAGE, THERE IS NO CLEAR INDICATION OR LABEL SHOWN WHEN A PRODUCT IS OUT OF STOCK, WHICH CAN MISLEAD USERS ABOUT PRODUCT AVAILABILITY.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION
STEP 2: NAVIGATE TO PRODUCT DETAIL PAGE
STEP 3: CHECK PRODUCT AVAILABILITY STATUS
STEP 4: OBSERVE IF OUT OF STOCK MESSAGE IS DISPLAYED
EXPECTED RESULT | SYSTEM SHOULD CLEARLY DISPLAY "OUT OF STOCK" STATUS FOR UNAVAILABLE PRODUCTS
ACTUAL RESULT | NO OUT OF STOCK MESSAGE OR INDICATOR IS DISPLAYED
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | UI DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1sr7ZooHR2vEqhJzeE1dhlwkiVRSg5WLI/view?usp=drive_link
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | ACER ONE 14
OS | WINDOWS
OS VERSION | 11
BROWSER | BRAVE

## DEFECT_09
DEFECT_ID | DEFECT_09
MODULE | PRODUCT LISTING / CART
SUMMARY | ADD TO CART OPTION IS NOT AVAILABLE FOR USED PHONE PRODUCT
DESCRIPTION | ON THE CELL PHONES PRODUCT LISTING PAGE, THE ADD TO CART BUTTON IS MISSING FOR THE "USED PHONE" PRODUCT, EVEN THOUGH THE PRODUCT IS DISPLAYED WITH PRICE AND SHOULD BE AVAILABLE FOR PURCHASE.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION
STEP 2: NAVIGATE TO ELECTRONICS > CELL PHONES
STEP 3: LOCATE THE "USED PHONE" PRODUCT
STEP 4: CHECK FOR ADD TO CART BUTTON
EXPECTED RESULT | ADD TO CART BUTTON SHOULD BE DISPLAYED FOR THE USED PHONE PRODUCT
ACTUAL RESULT | ADD TO CART BUTTON IS NOT DISPLAYED FOR THE USED PHONE PRODUCT
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1nalTTySkBT0GUhRo1HFxpzPdKbIurgNc/view?usp=drive_link
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | ACER ONE 14
OS | WINDOWS
OS VERSION | 11
BROWSER | BRAVE

## DEFECT_10
DEFECT_ID | DEFECT_10
MODULE | FOOTER / FOLLOW US
SUMMARY | RSS LINK IN FOLLOW US SECTION IS NOT WORKING
DESCRIPTION | IN THE FOOTER SECTION UNDER FOLLOW US, THE RSS LINK IS NOT FUNCTIONING PROPERLY AND DOES NOT REDIRECT TO THE EXPECTED RSS PAGE OR FEED.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION
STEP 2: SCROLL DOWN TO THE FOOTER SECTION
STEP 3: LOCATE FOLLOW US SECTION
STEP 4: CLICK ON RSS LINK
EXPECTED RESULT | RSS LINK SHOULD REDIRECT TO A VALID RSS FEED PAGE
ACTUAL RESULT | RSS LINK DOES NOT WORK OR DOES NOT REDIRECT CORRECTLY
SEVERITY | MINOR
PRIORITY | MEDIUM
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1E4af4NDXd91uHLQUSMNIVYp3-kOBv_AH/view?usp=drive_link
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | ACER ONE 14
OS | WINDOWS
OS VERSION | 11
BROWSER | BRAVE

## DEFECT_11
DEFECT_ID | DEFECT_11
MODULE | SEARCH FUNCTIONALITY
SUMMARY | SEARCH BAR IS NOT RETURNING RESULTS FOR VALID KEYWORDS
DESCRIPTION | THE SEARCH FUNCTIONALITY IS NOT WORKING PROPERLY. WHEN VALID KEYWORDS ARE ENTERED IN THE SEARCH BAR, THE SYSTEM DISPLAYS "NO PRODUCTS WERE FOUND" EVEN THOUGH RELEVANT PRODUCTS EXIST.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION
STEP 2: ENTER A VALID KEYWORD IN SEARCH BAR (E.G., COMPUTERS)
STEP 3: CLICK ON SEARCH BUTTON
EXPECTED RESULT | SYSTEM SHOULD DISPLAY RELEVANT PRODUCTS BASED ON SEARCH KEYWORD
ACTUAL RESULT | SYSTEM DISPLAYS "NO PRODUCTS WERE FOUND THAT MATCHED YOUR CRITERIA"
SEVERITY | CRITICAL
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1EY7x9SuVu9wtJ_c1uHx6rwQAiRgUnOQE/view?usp=drive_link
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | ACER ONE 14
OS | WINDOWS
OS VERSION | 11
BROWSER | BRAVE
BROWSER VERSION | 1.88.136
BUILD VERSION

## DEFECT_12
DEFECT_ID | DEFECT_12
MODULE | CHECKOUT / AUTHENTICATION
SUMMARY | USER IS ABLE TO PURCHASE PRODUCT WITHOUT LOGIN OR REGISTRATION
DESCRIPTION | THE SYSTEM ALLOWS USERS TO PROCEED WITH PURCHASE AND COMPLETE CHECKOUT WITHOUT REQUIRING LOGIN OR REGISTRATION, WHICH VIOLATES EXPECTED AUTHENTICATION RULES.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION
STEP 2: ADD ANY PRODUCT TO THE CART
STEP 3: NAVIGATE TO CART PAGE
STEP 4: CLICK ON CHECKOUT
STEP 5: PROCEED WITHOUT LOGIN OR REGISTRATION
EXPECTED RESULT | SYSTEM SHOULD REQUIRE USER TO LOGIN OR REGISTER BEFORE PROCEEDING WITH PURCHASE
ACTUAL RESULT | USER IS ABLE TO COMPLETE PURCHASE WITHOUT LOGIN OR REGISTRATION
SEVERITY | CRITICAL
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1bFBE1CU0Wim00hJt_JSsztXktNJQSC_o/view?usp=drive_link
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | ACER ONE 14
OS | WINDOWS
OS VERSION | 11
BROWSER | BRAVE
BROWSER VERSION | 1.88.136
BUILD VERSION

## DEFECT_13
DEFECT_ID | DEFECT_13
MODULE | SHIPPING / CHECKOUT
SUMMARY | USER IS ABLE TO ESTIMATE SHIPPING WITHOUT SELECTING COUNTRY
DESCRIPTION | IN THE ESTIMATE SHIPPING SECTION, THE SYSTEM ALLOWS USERS TO CALCULATE SHIPPING COST WITHOUT SELECTING A COUNTRY, WHICH SHOULD BE A MANDATORY FIELD FOR ACCURATE SHIPPING CALCULATION.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION
STEP 2: ADD A PRODUCT TO THE CART
STEP 3: NAVIGATE TO THE SHOPPING CART PAGE
STEP 4: GO TO ESTIMATE SHIPPING SECTION
STEP 5: DO NOT SELECT ANY COUNTRY
STEP 6: CLICK ON ESTIMATE SHIPPING
EXPECTED RESULT | SYSTEM SHOULD VALIDATE COUNTRY FIELD AND PROMPT USER TO SELECT A COUNTRY BEFORE ESTIMATING SHIPPING
ACTUAL RESULT | SYSTEM ALLOWS SHIPPING ESTIMATION WITHOUT SELECTING COUNTRY
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1Ats8VJ8v2LbtX4W5KWfJtj4u3Vdu_DEj/view?usp=drive_link
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | ACER ONE 14
OS | WINDOWS
OS VERSION | 11
BROWSER | BRAVE
BROWSER VERSION | 1.88.136
BUILD VERSION

## DEFECT_14
DEFECT_ID | DEFECT_14
MODULE | NAVIGATION BAR
SUMMARY | SPELLING OF JEWELLERY IS INCORRECT IN NAVIGATION BAR
DESCRIPTION | IN THE NAVIGATION BAR, THE CATEGORY NAME "JEWELLERY" IS MISSPELLED, WHICH AFFECTS UI QUALITY AND PROFESSIONAL APPEARANCE OF THE APPLICATION.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION
STEP 2: OBSERVE THE NAVIGATION BAR AT THE TOP
STEP 3: LOCATE THE JEWELLERY CATEGORY
EXPECTED RESULT | CATEGORY NAME SHOULD BE SPELLED CORRECTLY AS "JEWELLERY"
ACTUAL RESULT | CATEGORY NAME IS DISPLAYED WITH INCORRECT SPELLING
SEVERITY | MINOR
PRIORITY | LOW
DEFECT TYPE | UI DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1X1E1HhMOlsuN6mEqKKJGiwFGbWgjiYTx/view?usp=drive_link
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | ACER ONE 14
OS | WINDOWS
OS VERSION | 11
BROWSER | BRAVE
BROWSER VERSION | 1.88.136
BUILD VERSION

## DEFECT_15
DEFECT_ID | DEFECT_15
MODULE | PRODUCT DETAIL PAGE / REVIEWS
SUMMARY | USER IS NOT ABLE TO ADD REVIEWS FOR PRODUCTS
DESCRIPTION | THE SYSTEM DOES NOT ALLOW USERS TO SUBMIT REVIEWS FOR PRODUCTS. EVEN AFTER CLICKING ON ADD YOUR REVIEW AND ENTERING DETAILS, THE REVIEW IS NOT SUBMITTED OR SAVED.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION
STEP 2: NAVIGATE TO ANY PRODUCT DETAIL PAGE
STEP 3: CLICK ON ADD YOUR REVIEW
STEP 4: ENTER REVIEW DETAILS
STEP 5: SUBMIT THE REVIEW
EXPECTED RESULT | USER SHOULD BE ABLE TO SUCCESSFULLY SUBMIT AND VIEW THEIR REVIEW
ACTUAL RESULT | REVIEW IS NOT SUBMITTED OR DISPLAYED
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/18twQawH7VyUax7DFAlviefyh0fzP09pG/view?usp=drive_link
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | ACER ONE 14
OS | WINDOWS
OS VERSION | 11
BROWSER | BRAVE
BROWSER VERSION | 1.88.136
BUILD VERSION